## Task List
Task Name | QA Name | Developer Name | Planned QA Start Date | Planned QA End Date | Percentage of Complete
Release- 5/24/2017
Release of zipForm Plus with support for transaction oversight type affecting:XMPP/email notifications (approvals, e-signatures, etc), transaction list, template list, TASKS list, Dashboard metrics, Dashboard reports, dashboard map | Rony | Mark.Tatyana
Release- 5/31/2017
Turn off access by TLS 1.0 browsers (by IT configuration or code) in Plus and R | Rony
Release - 6/7/2017
Release of zipForm Plus with transaction type specificity for admins and TCs | Rony | Irik/Tatyana
Release of zipForm P lus with removal of SureClose integration | Malathi
Turn off access to legacy web serice to SureClose | Malathi
Release of zipForm Plus with cosmetic changes to Digital Ink Cybersecurity | Malathi
Release - 6/28
Release of zipForm Plus with ability to "Try new version" | Rony
Release of zipForm Plus with Cybersecurity changes (no KBA and one charge per transaction for SMS)
zipForm Plus Responsive
Release of zipForm Plus (responsive) with ability to go back to old UI | Malathi
Release of zipForm (responsive) with new login page | Malathi
Release of zipForm (responsive) with Cybersecurity changes (no KBA and one charge per transaction for SMS) | Malathi
(if not released earlier) Release of zipForm (responsive) with Collaboration with shortcuts from Parties and Documents | Rony | Mark
(if not released earlier) Release of zipForm (responsive) with Community, including handling of access to old vs new | Rony | Mark
Release of zipForm (responsive) with Public Sharing of Documents | Malathi | Mark
Release of zipForm (responsive) with public access to shared document along with auditing of visits and auditing of access to publicly shared documents | Rony | Mark/Tatyana
Release of zipForm Plus (responsive) with Chat in Collaboration | Rony | Mark
Release of zipForm (responsive) with support for DnD to move forms/documents in folders, create document versions, fill placeholder | Neha | Akshay | 2017-05-16 | 2017-05-19
Release of zipForm (responsive) with support for E-sign document upload from cloud sources | Neha
Release of zipForm (responsve) with enhanced notifications control in user profile | Chaithra | Matt
Release of zipForm (responsive) with embedding of Digital Ink signer UI in Community | Rony | Max
Release of zipForm (responsive) with Broker Management: Users, Offices, Teams, Permissions, etc | Neha
Release of zipForm Responsive with broker dashboard and reports | Chaithra/Malathi | Mark/Claude | 2017-05-15
Release of zipForm Responsive with Agent and TC dashboard and reports | Chaithra/Malathi | Claude/Sukrut
Release of zipForm Responsive with transaction retention dashboard | Neha | Ruth
Release of zipForm Resonsive with broker broadcast | Malathi | Mark
Release of zipFOrm responsive with Services access through transaction dashboard | Malathi
Release of zipForm Mobile (responsive) with BombBomb integration | Malathi | Matt
Release of zipForm Responsive with Guided Help throughout | Neha | Ratheesh,Sooria,Krishna,Venkat,Akshay
Release of zipForm responsive with partner integrations: RPR, DTR | Malathi | Matt
Release of zipForm Responsive with zipConsult (AnyMeeting integration) (IF KEPT) | Malathi | Matt
Release of zipForm Responsive with Forms Advisor integration | Malathi | Ruth
Release of zipForm Responsive with Quick Digital Ink transaction creation | Rony | Max
Release of zipForm (responsive) with direct access to forms with unnamed transaction and ability to print/send without saving (other functions prompt to save transaction first) | Malathi
Release of zipForm Responsive with support for Standalone team management/operation | Rony | Matt
Release of zipForm Responsive with support for CAR ads | Rony | Matt
Release of zipForm Responsive with support for broker skins and association banners | Rony
Release of zipForm Responsive with complete mini-order process for ancillary products (where applicable) including MLS Connect (through MLS Push), Digital Ink, Mobile, etc. | Malathi | Matt
Release of zipForm Responsive with NAR interstitial page (for direct logins NOT through try new UI) | Malathi | Matt
Release of zipForm Plus with support for renewals (streamlined, non-dues items) | Rony
Release of zipForm Responsive with upper modules functionality (if still applicable) | Rony
Release of zipForm Responsive with notifications upon transaction status change | Rony | Mark
Release of zipForm (responsive) with reassignment of unsassigned transactions | Chaithra | Irik
Release of zipForm (responsive) with support for transaction oversight type affecting:XMPP/email notifications (approvals, e-signatures, etc), transaction list, template list, TASKS list, Dashboard metrics, Dashboard reports, dashboard map | Rony | Mark/Tatyana
Releae of zipForm (responsive) with spell checker in outbound emails and for single/multiple form checking
(TENTATIVE) Release of zipForm Responsive with Trash folder access management
(TENTATIVE) Release of zipForm responsive with new hierarchy in Services tab
zipForm Mobile Responsive
Release of zipForm Mobile (responsive) with Collaboration/Share with shortcuts from Parties and Documents | Rony
Release of zipForm Mobile (responsive) with Community, including handling of access to old vs new | Rony
Release of zipForm Mobile (responsive) with Public Sharing of Documents | Rony
Release of zipForm Mobile (responsive) with public access to shared document along with auditing of visits and auditing of access to publicly shared documents | Rony
Release of zipForm Mobile (responsive) with embedding of Digital Ink signer UI in Community | Rony
Release of zipForm Mobile responsive with broker dashboard | Chaithra/Malathi
Release of zipForm Mobile responsive with Agent dashboard | Chaithra/Malathi
Release of zipForm Mobile Resonsive with Guided Help throughout | Neha
Release of zipFOrm responsive with Services access through transaction dashboard | Malathi
Release of zipForm (responsive) with BombBomb integration | Malathi
Release of zipForm Mobile responsive with partner integrations: RPR, DTR | Malathi
Release of zipForm Mobile (responsve) with enhanced notifications control in user profile | Chaithra
Release of zipForm Mobile (responsive) with support for E-sign document upload from cloud sources | Neha
Release of zipForm Mobile (responsive) with support for DnD to move forms/documents in folders, create document versions, fill placeholder | Neha
Release of zipForm Mobile (responsive) with SMS-based password recovery and related user profile Mobile number update | Rony
Release of zipForm Mobile Responsive with support for broker skins and association banners | Rony
Release of zipForm Mobile (responsive) with reassignment of unsassigned transactions | Chaithra
Release of zipForm Mobile with Quick Digital Ink transaction from transaction list | Rony
Release of zipForm Mobile (responsive) with direct access to forms with unnamed transaction and ability to print/send without saving (other functions prompt to save transaction first) | Malathi
Release of zipForm Mobile (responsive) with support for transaction oversight type affecting:XMPP/email notifications (approvals, e-signatures, etc), transaction list, template list, TASKS list, Dashboard metrics, Dashboard reports, dashboard map | Rony
Releae of zipForm Mobile (responsive) with spell checker in outbound emails and for single/multiple form checking | Neha
Release of zipForm Mobile Responsive with complete mini-order process for ancillary products (where applicable) including MLS Connect (through MLS Push), Digital Ink, Mobile, etc. | Malathi
(TENTATIVE) Release of zipForm Mobile (responsive) with support for renewals (streamlined, non-dues items)
(TENTATIVE) Release of zipForm Mobile (responsive) with Broker Management: Users, Offices, Teams
(TENTATIVE) Release of zipForm Mobile responsive with Trash folder access management
(TENTATIVE) Release of zipForm responsive with new hierarchy in Services tab
P
F
NT
NA

## Guided Help
TC No. | Test Scenarios | Bug # | Status | Test Case | Test Conditions | Expected Result | Remarks
Transaction Page
1 | Guided help on Transaction page |  | N/A | Disable guided help in profile | Go to profile settings to disable the feature | Guided help icon should not display on any pages. | This option is removed as per new requirement. | 0
2 | Guided help on Transaction page |  | P | Show help to create new transaction | 1. New transaction focus window | Should show description with navigation steps in sequence. |  | 1
3 | Guided help on Transaction page |  | P |  | 2. Focus to select Trasnaction Type |  |  | 1
4 | Guided help on Transaction page |  | P |  | 3. Transaction name & Property type |  |  | 1
5 | Guided help on Transaction page |  | P |  | 4. Focus on [optional] MLS connect |  |  | 1
6 | Guided help on Transaction page |  | P |  | 5. Save transaction. |  |  | 1
7 | Guided help on Transaction page |  | P | Show help to use form | 1. Focus on New form window. | Should show description with navigation steps in sequence. |  | 1
8 | Guided help on Transaction page |  | P |  | 2. My forms shows saved forms. |  |  | 1
9 | Guided help on Transaction page |  | P |  | 3. All forms to add more forms. |  |  | 1
10 | Guided help on Transaction page |  | P |  | 4. Fullscreen form. |  |  | 1
11 | Guided help on Transaction page |  | P |  | 5. Fastfill fields |  |  | 1
12 | Guided help on Transaction page |  | P |  | 6. [optional] MLS connect to import MLS listing information to form |  |  | 1
13 | Guided help on Transaction page |  | P | Show help to use my profile | 1. Focus on name. | Should show description with navigation steps in sequence. |  | 1
14 | Guided help on Transaction page |  | P |  | 2. Click profile. |  |  | 1
15 | Guided help on Transaction page |  | P |  | 3. Update details like email,fax,username, etc |  |  | 1
16 | Guided help on Transaction page |  | P |  | 4. Update email signature. |  |  | 1
17 | Guided help on Transaction page |  | P |  | 5. Update additional info such as DI/Docusign credentials. |  |  | 1
18 | Guided help on Transaction page |  | P | Click on import and open guided help |  | While importing txn, guided help should be non-interactive. |  | 1
19 | Guided help on Transaction page | 8676 | F | Click on Export and open guided help |  | Should display some warning message 'Please close the export' |  | 2
20 | Guided help on Transaction page | 8676 | F | Click on Delete and open guided help |  | Should display some warning message 'Please close the delete' |  | 2
21 | Guided help on Transaction page | 8676 | F | Click on Set approval and open guided help |  | Should display some warning message 'Please close transaction approval' |  | 2
22 | Guided help on Transaction page |  | P | Click on Transfer and open GH |  | While transferring txn, guided help should be non-interactive. |  | 1
23 | Guided help on Transaction page |  | P | Using clause manager |  | Guided help should not interative. |  | 1
24 | Guided help on Transaction page |  | P | Using look up field manager |  | Guided help should not interative. |  | 1
25 | Guided help on Transaction page |  | P | Using Mortgage calculator |  | Guided help should not interative. |  | 1
26 | Guided help on Transaction page | 8763 | F | Using view forms |  | GH - Simple form features should show the steps to user. | Simple form feature does not respond on page. | 2
27 | Guided help on Transaction page |  | P | Using Form advisor |  | Guided help should not interative. |  | 1
28 | Guided help on Transaction page |  | P | Open Guided help on transaction menu option |  | Guided help should not interative. |  | 1
29 | Guided help on Transaction page |  | P | Verify GH when view changes for transaction list |  | GH flow should show all the correct steps. |  | 1
30 | Guided help on Transaction page |  | P | Apply filter and verify GH |  | GH flow should show all the correct steps. |  | 1
31 | Guided help on Transaction page |  | P | On search verify GH |  | GH flow should show all the correct steps. |  | 1
32 | Guided help on Transaction page |  | P | Sort the order and verify GH |  | GH flow should show all the correct steps. |  | 1
33 | Guided help on Transaction page |  | P | Verify GH on Transaction shared by me using drop down list |  | GH flow should show all the correct steps. |  | 1
34 | Guided help on Transaction page |  | P | Verify other users txn |  | GH flow should show all the correct steps. |  | 1
35 | Guided help on Transaction page |  | P | Verify users which doesn't have permission to add transactions |  | GH flow will show upto Step 2 and permission warning message should display. |  | 1
36 | Guided help on Transaction page |  | P | Verify GH on All transactions |  | GH flow should show all the correct steps. |  | 1
37 | Verify above GH cases for BA role |  | P | BA role |  | Above all cases should shown correct. |  | 1
38 | Verify above GH cases for Agent role |  | P | Agent role |  | Above all cases should shown correct. |  | 1
39 | Verify above GH cases for TC role | 8625 | P | TC role |  | Above all cases should shown correct. |  | 1
40 | Verify above GH cases for LA role |  | P | LA/OA role |  | Above all cases should shown correct. |  | 1
Template Page
41 | Guided help on Template page |  | P | Show help to create a new template |  | GH from Step 1-8 should continue without any breakage. |  | 1
38 | Guided help on Template page |  | P | Click on import and open guided help |  | While importing Template, guided help should be non-interactive. |  | 1
39 | Guided help on Template page |  | P | Click on export and open guided help |  | While exporting Template, guided help should be non-interactive. |  | 1
40 | Guided help on Template page |  | P | Open GH while deleting template |  | While Deleting Template, guided help should be non-interactive. |  | 1
41 | Guided help on Template page |  | P | Open GH when templates menu option |  | GH should not be interactive. |  | 1
42 | Guided help on Template page |  | P | Open GH on clause |  | GH should not be interactive. |  | 1
43 | Guided help on Template page |  | P | Apply filter and open GH |  | Should show the correct workflow |  | 1
44 | Guided help on Template page |  | P | Sort and Open GH |  | Should show the correct workflow |  | 1
45 | Guided help on Template page |  | P | Search with text and open GH |  | Should show the correct workflow |  | 1
0
Transaction Summary/dashboard Page
0
46 | Guided help on open Transaction |  | P | Show help to store forms and documents for transaction | 1. click on Add documents. | Should show description with navigation steps in sequence. |  | 1
47 | Guided help on open Transaction |  | P |  | 2. Show up the transaction expiray date or choose different date from calendar. |  |  | 1
48 | Guided help on open Transaction |  | P |  | 3. Documents can be add using transaction detailed menu. |  |  | 1
49 | Guided help on open Transaction |  | P |  | 4. Docs can be save for trasnaction/as PDF. |  |  | 1
50 | Guided help on open Transaction |  | P |  | 5. Doc can also be shared online using share button. |  |  | 1
51 | Guided help on open Transaction |  | P | Show help to use zipvault | 1. Select doc to send Email using send button. | Should show description with navigation steps in sequence. |  | 1
52 | Guided help on open Transaction |  | P |  | 2. Select doc to send Fax using send button. |  |  | 1
53 | Guided help on open Transaction |  | P |  | 3. Use zipvault option using doc menu option. |  |  | 1
54 | Guided help on open Transaction |  | P |  | 4. Add contacts/import contact from address book. |  |  | 1
55 | Guided help on open Transaction |  | P |  | 5. Enter subject and body text and send email/fax. |  |  | 1
56 | Guided help on open Transaction |  | P | Show help to use ziplogix Digitalink | 1. Click on E-sign button. | Should show description with navigation steps in sequence. |  | 1
57 | Guided help on open Transaction |  | P |  | 2. Create a new signature packet |  |  | 1
58 | Guided help on open Transaction |  | P |  | 3. Add document if not avalable. |  |  | 1
59 | Guided help on open Transaction |  | P |  | 4. Name the signature packet. |  |  | 1
60 | Guided help on open Transaction |  | P |  | 5. Select forms using Add document button. |  |  | 1
61 | Guided help on open Transaction |  | P |  | 6. Upload doc from computer using browse button. |  |  | 1
62 | Guided help on open Transaction |  | P |  | 7. Add signer and finish. |  |  | 1
63 | Guided help on open Transaction |  | P | Show help to check status of ziplogix Digitalink submission | 1. click on signed packet. | Should show description with navigation steps in sequence with info. |  | 1
64 | Guided help on open Transaction |  | P |  | 2. View details, In progress shows when forms are in progress. |  |  | 1
65 | Guided help on open Transaction |  | P |  | 3. Status : completed on e-signer completion. |  |  | 1
66 | Guided help on open Transaction |  | P | Show help to create transaction parties | 1. Click on New,select Role. | Should show description with navigation steps in sequence with info. |  | 1
67 | Guided help on open Transaction |  | P |  | 2. Add contact/Import . |  |  | 1
68 | Guided help on open Transaction |  | P |  | 3. Save as contact,view in contact list. |  |  | 1
69 | Guided help on open Transaction |  | P | Show help to set due dates | 1. Select doc dates | Should show description with navigation steps in sequence with info. |  | 1
70 | Guided help on open Transaction |  | P |  | 2. Choose any type - fixed,none, relative |  |  | 1
71 | Guided help on open Transaction |  | P |  | 3. Choose status for doc and save |  |  | 1
72 | Guided help on open Transaction |  | P | Show help to use notes | 1. Add new notes and save. | Should show description with navigation steps in sequence with info. |  | 1
73 | Guided help on open Transaction |  | P |  | 2. Pick any note to send email. |  |  | 1
74 | Guided help on open Transaction |  | P |  | 3. Select notes to save as PDF. |  |  | 1
75 | Guided help on open Transaction |  | P |  | 4. Choose note and Print |  |  | 1
76 | Guided help on open Transaction |  | P | Show help to use history |  | Should listed here all recent activity. |  | 1
77 | Guided help on open Form page |  | P | Show help to work on my forms | 1. 'My forms' selection shows all the forms used in trasnactions,to open click that form. | Should show description with navigation steps in sequence with info. |  | 1
78 | Guided help on open Form page |  | P |  | 2 'All forms' shows all forms avaialble into library. |  |  | 1
79 | Guided help on open Form page |  | P |  | 3. Fullscreen use to display in larger format. |  |  | 1
80 | Guided help on open Form page |  | P |  | 4. Fastfill used to save quick details into forms |  |  | 1
81 | Guided help on open Form page |  | P |  | 5. [optional] MLSconnect to import MLS listing info into trasnactions. |  |  | 1
82 | Guided help on open Form page |  | P | Set approval for forms | while view click on set approval and choose the options. | Status should get changed as requested. |  | 1
83 | Verify Guided help model functionality | 8575 | P | Show Transaction help |  | While view help buttons and links should not allow to create |  | 1
84 | Verify GH on Transaction summary page as BA |  | P | Features in transaction summary |  | Should navigate help from Step 1-10 in sequence. |  | 1
85 | Transaction summary GH as Agent |  | P | Features in transaction summary |  | Should navigate help from Step 1-10 in sequence. |  | 1
86 | Transaction summary GH as TC |  | P | Features in transaction summary |  | Should navigate help from Step 1-10 in sequence. |  | 1
87 | Txn dashboard GH steps | 8574 | P | Verify steps |  | Should not skip any steps with page related. |  | 1
88 | Txn dashboaard GH verify with all types of transaction | 8653 | P | Listing,Lease,Purchase,Lease-Listing type |  | Should show description with navigation steps in sequence with info. |  | 1
89 | Txn dashboard page layout | 8683 | P | On page scroll |  | Should show the perfect visiblity while show help to user. |  | 1
90 | Txn dashboard GH |  | P | Verify next and previous button |  | Should work as featured. |  | 1
91 | Txn dashboard GH |  | P | Verify End Tour |  | Should terminate help model immediately |  | 1
92 | Verify GH on transaction menu drop down |  |  | from left menu corner |  | GH should not be interactive. |  | 0
93 | Change the status of transaction and verify GH |  |  |  |  | Should work as featured. |  | 0
94 | Verify GH UI when switching between tabs | 8719 | P |  |  | Should work good as per UI perspective |  | 1
0
| Parties tab | [6 empty] | 0
95 | Guided help on parties tab |  | P | Add new party |  | Should show the workflow with help models correctly |  | 1
96 | Guided help on parties tab |  | P | Add parties while GH |  | Should not allow to add new parties. |  | 1
97 | Verify UI on GH | 8714 | P |  |  | Should show the perfect visiblity while show help to user. |  | 1
98 | Verify GH on batch delete |  | P | parties batch deletion |  | Should show the workflow with help models correctly |  | 1
99 | Verify GH on share with parties |  | P |  |  | Should redirects to share page with different help options |  | 1
100 | Verify GH on apply filter parties |  | P |  |  | Should show the workflow with help models correctly |  | 1
101 | Verify GH on view changes |  | P |  |  | Should show the workflow with help models correctly |  | 1
| Documents tab | [6 empty] | 0
102 | Guided help on document page |  | P | Verify Add document help |  | Should open the help model and navigate correctly |  | 1
103 | Guided help on document page |  | P | Verify tiles icon while GH |  | Should be non interactive. |  | 1
104 | Guided help on document page |  | P | Verify Next and Previous button |  | Should works correct to use back and forward steps. |  | 1
105 | Guided help on document page |  | P | Verify End tour |  | Should terminate help immediately. |  | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| PASSED | 102 | 96.23% |  |  |  |  | 0
| FAILED | 4 | 3.774%
| UNTESTED | 0 | 0%
| CASES | 106 | 100%

## BA Dashdoard
TC No. | Test Scenarios | Bug # | Status | Test Case | Test Conditions/Test Steps | Expected Result | Remarks
1 | UI of Broker Admin Dashboard | 8460 | F | All Offices Drop down | Ensure offices assigned to the user in Administration module | All the offices listed in Office list under Administration menu should be listed in the drop down
2 |  |  | P | Monthly Transaction Charts | Transactions should be created and available in transaction tab | Data on transaction count and total listing/purchase price of Active, Closed, Expired, Fell through transactions should be displayed. Graph will be displayed as Day of Month vs No. of Transactions.
3 |  |  | P | Recent Activity |  | Transaction status changes, creation , deletion , approval activities should be captured here
4 |  |  | P | Approval Status Count Tiles for Transaction, Document and Task |  | Count of Approval request for Transaction, Document and Task should be displayed in respective tiles
5 |  |  |  | zipTMS™ Tasks |  | Count of tasks that are Not Started, In Progress and Overdue should be displayed
6 |  |  |  | Revenue Bar Graph |  | Should display the Active and Pending Transaction Revenue statistics in Bar Graph
7 |  |  |  | zipTMS™ Transaction Dates Tiles |  | Count of upcoming listing expiry dates, closing dates and rentention dates for the current month should be displayed here
8 |  |  |  | Quarterly Performance Snapshot |  | Quarterly sales report per user should be displayed
9 |  |  |  | Account Information |  | Account information should be diplayed
10 |  |  |  | Listing Map Property Type |  | Types of properties should displayed with color code in pie chart
11 |  |  |  | Listing Map Transaction Type |  | Types of transaction should displayed with color code in pie chart
12 |  |  |  | Map area |  | Should display all the properties of transactions with valid address with markers
13 |  |  |  | Search box and button |  | Should be able to search property on clicking Search button
14 | Monthly Transaction Charts |  | P | New Listings |  | Should display no. of new listing transactions and its total listing price for the current month in this tab. It should also have a report link next New Listing header
15 |  |  | P | Report link |  | Clicking on the link displays the reports window with the report of New Listings
16 |  |  | P | Closed Transactions |  | Should display no. of closed listings and its total purchase price for the current month in this tab. It should also have a report link next Closed Transaction header
17 |  |  | P | Report link |  | Clicking on the link displays the reports window with the report of Closed Transactions
18 |  |  | P | Expired Transactions |  | Should display no. of transactions that has crossed closing date but not yet closed. Its total purchase pirce should also be displayed. It should also have a report link next Expired Transaction header
19 |  |  | P | Report link |  | Clicking on the link displays the reports window with the report of Expired Transactions
20 |  | 8437 | F | Fell Through Transactions |  | Should display no. of fell through and its total purchase price in this tab. It should also have a report link next Fell Through Transaction header
21 |  |  | P | Report link |  | Clicking on the link displays the reports window with the report of Fell Through Transactions
22 | Recent Activity |  | P | UI of Recent Activity layout |  | Should display user profile image, Description of activity performed and of activity
23 |  |  |  | Activity logs for following activities
24 |  |  | P | Create a new Transaction |  | Should show into the activity field on top along with username.
25 |  |  | P | Send request approval for document/Transaction |  | Should be shown with username and document linked to particular transaction.
26 |  |  | P | Not approved for doc |  | "
27 |  |  | P | Clear status |  | "
28 |  |  | P | Approved the document |  | Should be shown with username and document linked to particular transaction.
29 |  |  | P | Delete transaction |  | Should show into the activity field on top along with username.
30 |  |  |  | Edit transaction status |  | Should show into the activity field on top along with username.
31 |  | 8436 | F | : Active |  | "
32 |  | 8436 | F | : Inactive |  | "
33 |  | 8436 | F | : Pending |  | "
34 |  | 8436 | F | : Closed |  | "
35 |  | 8436 | F | : Prospect |  | "
36 |  | 8436 | F | : Fell Through |  | "
37 |  |  | P | Change profile photo and edit trasnaction |  | Should show activity feeds with updated profile picture
38 |  |  | P | Remove profile photo and keep default |  | Should show the default photo with activity feeds.
39 |  |  | P | Activity logs of members of brokerage |  | Activity logs of location admin, agents and TC should also be displayed for BA
40 |  |  | P | Document and transaction Names as link |  | Document name and transaction names should be displayed as link, clicking on which should land on Transaction dashboard page
41 |  | 8447 | F | See More link |  | On clicking this link should display more activity logs
42 | Approval Status Count Tiles |  | P | UI of Approval Status Tiles |  | Tile should contain tile icon for transaction/document/task, count of request and link leading to report
43 |  |  | P | Transactions to Approve |  | Count of transactions that need approval is displayed
44 |  |  | P | Documents to Approve |  | Count of documents that need approval is displayed
45 |  | 8446 | F | Tasks to Approve |  | Count of tasks that need approval is displayed
46 | Zip TMS Monthly Activities |  |  | Tasks Not Started |  | No. of tasks that are in status Not Started should be displayed, this should match with Task tab total no. of tasks in Not Started status
47 |  |  |  | Tasks In Progress |  | No. of tasks that are in progress should be displayed, this should match with Task tab total no. of tasks in progress
48 |  |  |  | Tasks Overdue |  | No. of tasks that are overdue should be displayed, this should match with Task tab total task overdue count
49 | Map Segment |  |  | All Office Droplist |  | All the offices listed in Office list under Administration menu should be listed in the drop down
50 |  |  |  | Property Type Color Codes |  | Types of properties should displayed with color code in pie chart
51 |  |  |  | Transaction Type Color Codes |  | Types of transaction should displayed with color code in pie chart
52 |  |  |  | Listing Map |  | Should display google map with property markers
53 |  |  |  | Zoom In | Scroll to Map | Should zoom In the map
54 |  |  |  | Zoom Out | Scroll to Map | Should zoom out the map
55 |  |  |  | Search Field and button | Search for Property Values | Should search the properties matching search criteria
56 | Revenue |  | P | Revenue Graph |  | Should display the Active Listing and Pending Transactions Price in Bar Graph
57 |  |  | P | Active Listings |  | Should display total price of active listings
58 |  |  | P | Pending transactions |  | Should display total price of pending transactions
59 |  | 8461 | F | Report link |  | Clicking on report link should display revenue details.
60 | zipTMS™ Monthly Transaction Dates | 8448 | F | Listings expiring |  | Transactions whose expiry date is current or upcoming dates of the current month are displayed
61 |  | 8448 | F | Transactions closing |  | Transactions whose closing date is current or upcoming dates of the current month are displayed
62 |  | 8448 | F | Retention expirations |  | Transactions whose retention date is current or upcoming dates of the current month are displayed
63 | Quarterly Performance |  |  | UI of Quarterly Performance |  | Should display name, Office, Closed transaction count and sales volume of members of brokerage
64 |  |  |  | Quarterly Performance data |  | Should display the total purchase price of closed transactions assigned for the user as sales volume
65 |  |  | P | Report link |  | Clicking on report link should display quarterly perfomance details.
66 | Account Info Summary |  | P | Users |  | User tab should display all the users with Role,Count and available
67 |  | 8452 | F | Form Libraries |  | Form libraries should display the data of description,available,used,total
68 |  | 8452 | F | Products |  | Products should display the data of description,available,used,total
69 |  |  | P | Report link |  | Clicking on report link should display reports of users/ form libraries/ product details.
70 | Accessibility |  |  | Accessibility |  | With the help of Wave tool when viewed there should not be any accessisibilty related issues
71 | Spanish Translation |  |  | Spanish translation |  | Every page should display in its equivalent Spanish translation script
72 | Reports |  | P | UI of the Report |  | Should include Return to Dashboard link, AllOffices dropdown, Reports dropdown, From and To Date pickers, Export as CSV button, Run Report button and Report details
73 |  |  | P | Return to Dashboard link |  | Clicking on this link, user should be taken to Dashboard. This link is only available to user if he has navigated to report window from Dashboard.
74 |  |  | P | All Office drop down |  | All the offices assigned to user should be listed here
75 |  |  | P | Reports drop down |  | Report list have following reports: Transaction/ Revenue New Listings Active Listings Pending Transactions Closed Transactions Expired Transactions Transactions Fell Account Reports Users/Role Licences Form Libraries Other Products Activity/Performance Agent Performances Transaction Activity Management/Oversight Transaction Approval Document Approval Task Approval Tasks Report
76 |  |  | P | From and To Date pickers |  | Should be displayed for picking from and to dates, by default the date span will be current month start and end dates
77 |  |  | P | Export as CSV button |  | Clicking on the button should download report data to CSV
78 |  |  | P | Run Report button |  | Selecting a report and clicking on this button should display reports details
79 |  |  |  | Report Lists details
80 |  |  | P | New Listings |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
81 |  |  | P | Active Listings |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
82 |  |  |  | Pending Transactions |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
83 |  |  |  | Closed Transactions |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
84 |  |  |  | Expired Transactions |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
85 |  |  |  | Transactions Fell |  | Report should display details like, Agent Name, Transaction Name, Address, Created, Transaction Type, Property Type, Status, Listing Date, Listing Expiration Date, Closing Date, Listing Price, Purchasse Price and ESCROW Number. Also Total Count, Listing Total and Purchase Total details.
86 |  |  |  | Users/ Role Licenses |  | Report should display details like, Name, Role, Library, Expiration
87 |  |  |  | Form Libraries |  | Report should display details like, Total Library Count, Description, Avaliable, Used, Total, Expiration
88 |  |  |  | Products |  | Report should display details like, Total Product Count, Description, Avaliable, Used, Total, Expiration
89 |  |  |  | Agent Performances |  | Report should display details like, Agent Name, Office, Closed Transaction count and Sales Valume
|  |  |  | Transaction Activity |  | TBD
|  |  |  | Transaction Approval |  | TBD
90 |  |  |  | Document Approval |  | Report should display details like, Transaction Name, Document Name, Type, Comment, Submitter, Submission Date
91 |  |  |  | Task Approval |  | TBD
92 |  |  |  | Task Report
93
94

## DnD Documents
TC No. | User Role | Test Scenarios | Bug # | Status | Test Case | Test Conditions | Expected Result | Remarks
1 | Broker Admin | DnD to move documents from system |  | P | Move a PDF document from local storage to main folder | Ensure PDF doc | Document should moved successfully into main folder. |  | 1
2 |  | DnD to move documents from system |  | P | Add a folder and Dnd doc |  | Document should moved successfully into the mentioned folder. |  | 1
3 |  | DnD to move documents from system |  | P | Add a subfolder and Dnd doc |  | Document should moved successfully into desired location. |  | 1
4 |  | Verify the Extension types file |  | P | Dnd doc with different extensions | .jpg | Dnd document Should move successfully. |  | 1
5 |  | Verify the Extension types file |  | P |  | .png | Dnd document Should move successfully. |  | 1
6 |  | Verify the Extension types file |  | P |  | .gif | Dnd document Should move successfully. |  | 1
7 |  | Verify the Extension types file |  | P |  | .pdf | Dnd document Should move successfully. |  | 1
8 |  | Verify the Extension types file |  | P |  | .doc | Dnd document Should move successfully. |  | 1
9 |  | Verify the Extension types file |  | P |  | .docx | Dnd document Should move successfully. |  | 1
10 |  | Verify the Extension types file |  | P |  | .xlt | Dnd document Should move successfully. |  | 1
11 |  | Verify the Extension types file |  | P |  | .xls | Dnd document Should move successfully. |  | 1
12 |  | Verify the Extension types file |  | P |  | .xlsx | Dnd document Should move successfully. |  | 1
13 |  | Verify the Extension types file |  | P |  | .bmp | Dnd document Should move successfully. |  | 1
14 |  | Verify the Extension types file |  | P |  | .txt | Dnd document Should move successfully. |  | 1
15 |  | Verify the Extension types file |  | P |  | .csv | Dnd document Should move successfully. |  | 1
16 |  | Verify the Extension types file |  | P |  | .rtf | Dnd document Should move successfully. |  | 1
17 |  | Verify the Extension types file |  | P |  | .zip | Dnd document Should move successfully. |  | 1
18 |  | Verify the Extension types file |  | P |  | .mp3 | Dnd document Should move successfully. |  | 1
19 |  | Verify the Extension types file |  | P |  | .ppt | Dnd document Should move successfully. |  | 1
20 |  | Verify the Extension types file |  |  |  | .pub | Dnd document Should move successfully. |  | 0
21 |  | Verify the Extension types file |  |  |  | .wma | Dnd document Should move successfully. |  | 0
22 |  | Verify the Extension types file |  | P |  | .mpg | Dnd document Should move successfully. |  | 1
23 |  | Verify the Extension types file |  | P |  | .flv | Dnd document Should move successfully. |  | 1
24 |  | Verify the Extension types file |  | P |  | .avi | Dnd document Should move successfully. |  | 1
25 |  | Verify the Extension types file |  | P |  | .m4a | Dnd document Should move successfully. |  | 1
26 |  | Verify the Extension types file |  | P |  | .mov | Dnd document Should move successfully. |  | 1
27 |  | Verify the Extension types file |  |  |  | .vts | Dnd document Should move successfully. |  | 0
28 |  | Verify the Extension types file |  |  |  | .xzfx | Dnd document Should move successfully. |  | 0
29 |  | Verify the Extension types file |  |  |  | .msg | Dnd document Should move successfully. |  | 0
30 |  | Verify the Extension types file |  |  |  | .pst | Dnd document Should move successfully. |  | 0
31 |  | Verify the Extension types file |  |  |  | .docm | Dnd document Should move successfully. |  | 0
32 |  | Verify the Extension types file |  |  |  | .dotx | Dnd document Should move successfully. |  | 0
33 |  | Verify the Extension types file |  | P |  | .pptx | Dnd document Should move successfully. |  | 1
34 |  | Verify the Extension types file |  | P |  | .pptm | Dnd document Should move successfully. |  | 1
35 |  | Verify the file max size |  |  | Dnd document with file size |  | Max size ahould allow upto 6MB |  | 0
36 |  | Rename file while Dnd |  | P | Dnd and rename file | check alphabets | Should accept the characters and saved successfully. |  | 1
37 |  | Rename file while Dnd |  | P |  | check numeric | Should accept the characters and saved successfully. |  | 1
38 |  | Rename file while Dnd |  | P |  | check alphanumeric | Should accept the characters and saved successfully. |  | 1
39 |  | Rename file with max characters | 8477 | P | Dnd and rename file | check with long text charaters such as >100 | Should not allow to type (>100) charaters in edit field. |  | 1
40 |  | DnD to move documents on locked txn |  | P | Verify Dnd doc for locked txn |  | Should not allow to drag and drop from local storage to documents. |  | 1
41 |  | DnD to fill placeholder | 8542 | P |  |  | Should not allow to fill placeholder using DnD. |  | 1
42 |  | Internal DnD to upload versions |  | P |  | Pick file to drag and drop | Should upload the version for document successfully. |  | 1
43 |  | Internal DnD to remove version | 8543 | P |  | Use Folder left panel to remove | Should remove the doc version. |  | 1
44 | TC User | DnD doc from local storage |  | P |  |  | Document should moved successfully into main folder. |  | 1
45 |  | DnD doc when TC doesn't have permission | 8596 | P |  |  | Should not allow to add files when TC doesn't have permission. |  | 1
46 |  | Verify with above file type |  | P |  |  | Should allow DnD with above all file type |  | 1
0
0
0
0
0
0
0
0
0
|  | PASSED | 37 | 100%
|  | FAILED | 0 | 0%
|  | UNTESTED | 0 | 0%
|  | CASES | 37 | 100%

## Users
TC No. | Test Scenarios | Bug # | Status | Test Case | Test Conditions | Expected Result | Remarks
1 | Add User as BA | 8490 | F | Add a new BA | Enter all mandatory fields | Should add the profile as BA. | By default agent is getting created instead of BA | 2
2 | Edit BA |  | P | Edit the profile BA | Update fields | Should edit and updated with new data. |  | 1
3 | Delete BA |  | P |  | Select BA and delete | Should get deleted from list. |  | 1
4 | Add a new agent |  | P | Add agent | Enter all mandatory fields | Should add the profile of Agent. |  | 1 | USER MANAGEMENT - BROKER | USER MANAGEMENT - BROKER
5 | Add a new LA | 8490 | F | Add LA | Enter all mandatory fields | Should add the profile of LA. | By default agent is getting created instead of LA | 2 | USER MANAGEMENT - BROKER | BA admin administration of DI tokens
6 | Search users |  | P | Search users with text | enter text to search | Should display the searched user with menu options. |  | 1 | USER MANAGEMENT - BROKER | BA can access agent's transactions
7 | Apply filters |  | P | Filter by location |  | Users should display associated to that particular location itself. |  | 1 | USER MANAGEMENT - BROKER | BA can edit and save agent's transactions
8 |  |  | P | Filter by Role |  | Only Associated roles user should display |  | 0 | USER MANAGEMENT - BROKER | BA can filter and sort agent's transactions
9 |  |  | P | Filter by status |  | Only belongs to status users should display. |  | 0 | USER MANAGEMENT - BROKER | BA can add agent, assign to an Office
10 | Clear All filters |  | P | Clear all |  | All selected filter should be removed and whole list data should be populated. |  | 1 | USER MANAGEMENT - BROKER | BA add office
11 | Verifying accessibility for BA |  | P | Access level for BA |  | BA can access agent's transactions. |  | 1 | USER MANAGEMENT - BROKER | BA can create/edit/delete clauses, templates
12 | Verifying accessibility for BA |  | P | Edit and save agents Txn |  | BA can edit and update the agents transactions |  | 1 | USER MANAGEMENT - BROKER | BA can delete agent
13 | [7 empty] | 0 | USER MANAGEMENT - BROKER | BA cab delete office
14 | [7 empty] | 0 | USER MANAGEMENT - BROKER | BA can edit agent
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can edit office
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA library manager
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA reassign agent's and pending transactions
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Reports - Transactions By User
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Reports - Seats By Library
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Reports - Transactions By Location
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can search agents within entire Brokerage
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can search agents within an Office
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can search offices
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can sort agents
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA sort agents (by criteria, office, etc)
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Can sort offices
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can View Other BA TXNs
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Edit Other BA TXNs
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Edit then Save another BA's TXN, Saved to Original BA account
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Email another BA's txn
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA cannot Delete another BA
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Delete OA
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Delete Agents
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Change BA, OA and Agents role to another
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA can Reset Password of users of all roles
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA while in another's BA Txn list creates new TXN, It is saved in logged in BA account
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA while in OA Txn list creates new TXN, It is saved in BA logged in account
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Copying there own TXN saves it to their own account
[8 empty] | 0 | USER MANAGEMENT - BROKER | BA Copying BA Txn saves it to BA's account
| PASSED | 8 | 80%
| FAILED | 2 | 20%
| UNTESTED | 0 | 0%
| CASES | 10 | 100%

## Browsers
CASE# | Bug # | PASS/FAIL | Feature | Test Setup/Conditions | Expected Result | NOTES
|  |  | BROWSER SUPPORT ON PC |  |  |  | 0
| 8583 | P | BROWSER SUPPORT ON PC | Windows 10 Edge IE11 | Smoke test all DnD related ICONs and Features |  | 1
|  | P | BROWSER SUPPORT ON PC | Windows 10 Chrome | Smoke test all DnD related ICONs and Features |  | 1
|  | P | BROWSER SUPPORT ON PC | Windows 10 FireFox | Smoke test all DnD related ICONs and Features |  | 1
|  | P | BROWSER SUPPORT ON PC | Windows 10 Safari | Smoke test all DnD related ICONs and Features |  | 1
|  | P | BROWSER SUPPORT ON PC | Windows 10 Opera | Smoke test all DnD related ICONs and Features |  | 1
0
0
|  |  | BROWSER SUPPORT ON Android- Responsive |  |  |  | 0
|  | N/A | BROWSER SUPPORT ON Android Mobile | Android browser 6.0 |  |  | 0
|  | N/A | BROWSER SUPPORT ON Android Mobile | Android Chrome |  |  | 0
|  | N/A | BROWSER SUPPORT ON Android Mobile | Android firefox |  |  | 0
|  | N/A | BROWSER SUPPORT ON Android Mobile | Android Opera mini |  |  | 0
0
|  |  | BROWSER SUPPORT ON iOS- Responsive |  |  |  | 0
|  | N/A | BROWSER SUPPORT ON iOS | MAC OSX10.12 Sierra Safari |  |  | 0
|  | N/A | BROWSER SUPPORT ON iOS | MAC OSX10.12 Sierra chrome |  |  | 0
|  | N/A | BROWSER SUPPORT ON iOS | MAC OSX10.12 Firefox |  |  | 0
0
0
0
0
0
0
0
0
0
0
0 | [6 empty] | 0
0 | [6 empty] | 0
| PASSED | 5 | 100%
| FAILED | 0 | 0%
| UNTESTED | 0 | 0%
| CASES | 5 | 100%

## Agent and TC Dashboard
Test Scenarios | Bug # | Status | Test Case | Test Conditions/Test Steps | Expected Result | Remarks
UI of Agent Dashboard

## Reassign unassigned Transaction
Test Scenarios | Bug # | Status | Test Case | Test Conditions/Test Steps | Expected Result | Remarks
Transfer button |  |  | Transfer button |  | Should display in nav bar, clicking on which should open Transfer Transaction Window
UI of Transfer |  |  | UI of Transfer Transaction |  | Should Display following: 1. Title of the window as